## Sheet1
Feature | Priority | Est Difficulty | Approach | Status
Make app UI discoverable for first-time users | HIGH | HIGH | Several approaches. 1: Include basic static tutorial information (e.g. 'Click button to load table info then drag fields to the selection buckets') 2: Display dynamic help information for getting a basic query off the ground (e.g. 'You added a field to the Values bucket. Add at least one column to rows/columns to trigger a pivot query.') 3: Add tooltips to interface elements. | Not Started
Implement query storage/retrieval and associated UI | HIGH | HIGH | Query information is already being updated in lockstep with user actions. Trivial to store query objects (in localstorage to start with). On retrieval, fire off the stored query object and rearrange selection bucket DOM to match object. DOM arrangement will require rewriting some code in client-side View module. | Not Started
Change Filter selection for Filters to be similar to excel, mulit-list check boxes | HIGH | HIGH/LOW | Listing all values on a field (like Excel) will require a DB query, severely degrading user experience with the speeds we have been seeing. On the flip side, allowing the user to combine multiple '___ OR ___' type criteria is low difficulty. | Not Started
Research: Can we reconstruct post-query client side adjustements to the pivot table, such as removing/renaming fields, when retrieving previous queries? | LOW | HIGH | Possibly. Best guess is to maintain an object describing transformations made to the 'base' pivot table returned from server, then applying transformations to a fresh copy of that query/table in a sensible order. There are a huge number of possible transformations that a user can make to the table, so this will be difficult to get 100% correct. Also we are concerned that this approach may not scale for future ways of displaying pivot table results. | Not Started
Display error to user when query times out on server. | HIGH | LOW | Unsure what message CodeIgniter sends internally when request times out. Worst-case, front-end code can catch the HTTP 500 error and build an error object to show the user. | Complete
Limitation - Cannot do multiple aggregators at the same time, for example Count of ID and SUM of ID where Year is rows | HIGH | LOW | This is no problem on the back end. Just need to adjust front-end validation to allow duplicate field in Values bucket | Complete
Count on just values when no rows or column values selected | HIGH | MED | Took this to mean 'only value(s) are selected'. Add logic to validation that does not reject this query configuration. This type of query will present a single row, COUNT(*). | Complete
Remove ability to drag-and-drop columns which contain row labels | HIGH | MED | N = length of rows array. First N elements of each row array do not have the sortable attribute. | Complete
Back-end mechanism to halt the query. | MED | HIGH | If the associated front-end mechanism works, do we need this functionality? The only downside to letting all requests complete on the back-end is that we are wasting DB queries. Otherwise, every server request is stateless so the requests don't affect each other. | Not Started
Mouse Pointer/curser when selecting a field and dragging is showing text field cursor | LOW | LOW | Adjust jquery properties for draggable container. | Complete
Fix 'column ambiguously defined' when aliasing long column values with aggregate fns | MED | LOW | Look at deprecated column aliasing function. Take longest aggregate alias into account. Can these names be made more friendly? Or perhaps add metadata to the response so client can insert pretty column names? | Not Started
Front-end mechanism to halt the query. | MED | MED | Each query is assigned a unique ID when it is sent to server. Client maintains a buffer of pending queries. When user signals to halt current queries, results of queries in the buffer will be discarded when they return from the server. Queries made after the 'halt' command will be treated as normal. | Not Started
Limitation - Can only do Rows and IDs not just Columns and IDs | MED | MED | Add logic to validation that does not reject this query configuration. This type of query will present a single row, COUNT(*) pivoted against SELECT DISTINCT column values. | Complete
Limitation - Removing Unwanted Rows | MED | MED | Can re-use logic from column removal/storage. Presents a good opportunity to clean up the UI for row/column storage. | Not Started
Ability to rename column row result values for first row /column (dropdowns are best) | MED | MED | Easy to rename table cells. Can't remember what is meant by 'dropdowns are best'. | Not Started
Revisit UX for double-click UI operations | MED | MED | To make the UI as discoverable as possible, should 'removal' operations currently mapped to double-click instead live within right-click menus? How about an on-hover 'X' button for removing fields? | Not Started

## Sheet2
FIELD LIST
SORT BUCKETS