## Sheet1
ID | Feature | Priority | Est Difficulty | Approach | Status | Started | Completed
6 | Limitation - Cannot do multiple aggregators at the same time, for example Count of ID and SUM of ID where Year is rows | HIGH | LOW | This is no problem on the back end. Just need to adjust front-end validation to allow duplicate field in Values bucket | Complete | 2017-08-25 | 2017-08-25
5 | Display error to user when query times out on server. | HIGH | LOW | Unsure what message CodeIgniter sends internally when request times out. Worst-case, front-end code can catch the HTTP 500 error and build an error object to show the user. | Complete | 2017-08-25 | 2017-08-25
26 | Allow user to toggle live fetching of pivot data from server | HIGH | LOW | Flag will bypass call to sendConfig() in pivotController.js | Complete | 2017-10-23 | 2017-10-23
33 | Relabel save/load buttons | HIGH | LOW | Load discard save save as | Complete | 2017-09-28 | 2017-09-28
35 | Remove legend from graphs | HIGH | LOW |  | Complete | 2017-10-12 | 2017-10-12
36 | Ability to query ANY table from given DB | HIGH | LOW | On page load, server asks DB for list of tables. Used to poplate window.availableTables. Works with save/load stystem | Complete | 2017-10-11 | 2017-10-12
28 | Move jQuery and other external libs onto server | HIGH | LOW | Enumerate all external libs | Complete | 2017-09-25 | 2017-09-25
20 | Add menu library to support item #s 2, 3, and context menus | HIGH | MED | Cancelled in favour of using JQueryUI's modal dialog() for #2 and #18, and expanding contextmenu.js library for #3 | Complete | 2017-08-18 | 2017-08-27
8 | Remove ability to drag-and-drop columns which contain row labels | HIGH | MED | N = length of rows array. First N elements of each row array do not have the sortable attribute. | Complete | 2017-08-28 | 2017-08-28
18 | Display chart representation of pivot table with chart.js. Simple bar/line charts for now. | HIGH | MED | Some data contortion required. Array of arrays not supported in the case of multiple aggregators. Also, what about case of non-numeric fields? (Labels will be improved with #11) | Complete | 2017-08-29 | 2017-08-30
7 | Count on just values when no rows or column values selected | HIGH | MED | Took this to mean 'only value(s) are selected'. Add logic to validation that does not reject this query configuration. This type of query will present a single row, COUNT(*). | Complete | 2017-08-18 | 2017-08-18
17 | Bug: identical Value entries cause 'column ambiguously defined' (e.g. COUNTOF_ID and COUNTOF_ID in Values bucket) | HIGH | MED | Reject queries with duplicate filter signatures on server-side validation step. This just tosses the server request; there's no reason to return a query containing dupe values. | Complete | 2017-10-24 | 2017-10-24
30 | Drag and drop sorting for row/cols | HIGH | MED | Sorting done through a dedicated UI element. | Complete | 2017-09-26 | 2017-09-27
31 | Row headers should appear hierarchical like col headers | HIGH | MED | For each included row, keep track of how many contiguous values there are for each label. When iterating through rows, only draw the label (with rowspan=contiguous) when coordinateIndex % contiguous === 0 | Complete | 2017-09-26 | 2017-09-26
32 | Row/Col totals | HIGH | MED | Like excel pivot tables. Rendering controlled by a flag, which we can add to the UI at a later point. | Complete | 2017-10-26 | 2017-10-26
34 | Add new database location | HIGH | MED | Current DB location is somewhat hard-coded. Need to refactor some stuff to make this work. | Complete | 2017-10-10 | 2017-10-11
37 | Bug: loading queries from a 'cold start' (no table/field cache) causes pivot and sortable elements to be removed after rendering | HIGH | MED | Examine sequencing of async table/retrieval fns. Do callbacks remove pivot/sortable elements? Worst case, write new fn for loading queries that incorporates table/field retrieval but without DOM destruction | Complete | 2017-10-25 | 2017-10-25
3 | Change Filter selection for Filters to be similar to excel, mulit-list check boxes | HIGH | HIGH | Dropping a field into the filter bucket triggers a SELECT UNIQUE to get the field's values from the table. Have been asked to retain SQL style queries. That code is not activated right now--need to refactor a bit before it can be readded. | Complete | 2017-09-28 | 2017-09-28
41 | Chart labels should reflect row/col labels from pivot table | HIGH | LOW | I think we're reading these labels from Model, not the transform. | Complete | 2017-11-10 | 2017-11-10
11 | Fix 'column ambiguously defined' when aliasing long column values with aggregate fns | HIGH | HIGH | On the server, alias column/reducer names to compact representation and keep hydration mappings that can be applied to the results returned from the DB. e.g. the string "2017" is replaced with random identifier "SDKJG" wherever it occurs in the query. Before passing results back to the client, replace all random identifiers with their 'real' string representations. Also allows us to represent results in a more sophisticated way than array-of-arrays. (The term for this new representation is 'expressive results') | Complete | 2017-08-29 | 2017-09-14
16 | Revisit UX for double-click UI operations | MED | LOW | Replace double-click delete actions with an on-hover 'X' button for removing fields. Use Jquery hover() | Complete | 2017-08-31 | 2017-08-31
13 | Limitation - Can only do Rows and IDs not just Columns and IDs | MED | MED | Add logic to validation that does not reject this query configuration. This type of query will present a single row, COUNT(*) pivoted against SELECT DISTINCT column values. | Complete | 2017-08-18 | 2017-08-18
14 | Limitation - Removing Unwanted Rows | MED | MED | Got this for free with expressive results/transformations. See #11 | Complete | 2017-09-18 | 2017-09-18
12 | Front-end mechanism to halt the query. | MED | MED | Each query is assigned a unique ID when it is sent to server. Client maintains a buffer of pending queries. When user signals to halt current queries, results of queries in the buffer will be discarded when they return from the server. Queries made after the 'halt' command will be treated as normal. | Complete | 2017-09-06 | 2017-09-06
27 | Should be able to both 'save' and 'save as' queries | MED | MED | Give saved models an ID, so that new saves can overwrite current 'file' or else do a 'save as…' | Complete | 2017-09-21 | 2017-09-21
38 | Sort pivot table by values, asc/desc | HIGH | MED | When sort-by-value is indicated (on an aggregator column cell), save row coord + agg coord + (asc ¦ desc) in a the transformation. If sort-by-value transformation key is found, create a sequence of {row-coord: Array, value: (Number ¦ String)} and then: natural sort the sequence on value key -> return a sequence of just the row coord keys. Then render the pivot table using this new row coord ordering rather than the one returned by the cartesian coords fn. | Complete | 2017-11-06 | 2017-11-09
39 | Add x-axis tick mark labels to chart | HIGH | MED | Added tick marks and improved legibility (with line breaks). Also fixed an issue where bars, tick marks, and tick mark text were misaligned. | Complete | 2017-11-10 | 2017-11-10
2 | Save/restore queries | MED | HIGH | Query information is already being updated in lockstep with user actions. Trivial to store query objects (in localstorage to start with). On retrieval, fire off the stored query object and rearrange selection bucket DOM to match object. DOM arrangement will require rewriting some code in client-side View module. | Complete | 2017-08-17 | 2017-08-29
23 | Changes in pivot table shape (e.g. removing rows/cols/resorting) should be reflected in charts | MED | HIGH | Changes currently modify DOM, not app state. Conversely, charts are generated from state (specifically most recently received pivot results). Need to pin shape modifications to state. See #11 | Complete | 2017-09-18 | 2017-09-18
15 | Ability to rename row/column/aggregator labels | MED | HIGH | Will register a new transform for remapping. | Complete | 2017-09-27 | 2017-09-28
10 | Mouse Pointer/curser when selecting a field and dragging is showing text field cursor | LOW | LOW | Adjust jquery properties for draggable container. | Complete | 2017-08-18 | 2017-08-18
24 | Arrange table fields and sorting buckets in vertical stack | LOW | LOW | Combine container divs. | Complete | 2017-09-01 | 2017-09-01
29 | Remove dead code from recently-changed libs | LOW | LOW | Affects tpivot and tchart | Complete | 2017-09-25 | 2017-09-25
25 | Restyle app for cohesive look and feel | LOW | MED | Redid UI to more closely match Excel ribbon idioms. Used bootstrap for element styles. | Complete | 2017-09-01 | 2017-09-06
40 | Change chart value tooltips to read "Foo" instead of "count(CASENUMBER) of Foo: $Value" | HIGH | MED | Can't remove value (e.g. the number for this row/col intersection) | Complete | 2017-11-10 | 2017-11-10
4 | Research: Can we reconstruct post-query client side adjustements to the pivot table, such as removing/renaming fields, when retrieving previous queries? | LOW | HIGH | Transformations have made this possible. Transforms are included with the data saved about a query. When loaded, the transform is pulled out and combined with the pivot result when it comes back from the server. | Complete | 2017-09-12 | 2017-09-21
43 | Possible bug: are charts reflecting/working with filters are selected? | HIGH | MED | This seems to be working? May be wonky with large filter sets applied. Will continute to monitor. | Complete | 2017-11-10 | 2017-11-10
21 | Refine presentation of charts, building on #18 | MED | MED | Need improvements to chart visuals: sort entires respecting numeric columns (but see #11), make bar charts more legible. Legends take up too much space at bottom of chart. Can charts be resized? Do charts respect label renaming? Also, charts do not work with length 0 aggregators. Configure chart properties | Complete | 2017-11-10 | 2017-11-10
47 | Chart title should be centered. | HIGH | LOW |  | Complete | 2017-11-20 | 2017-11-20
1 | Make app UI discoverable for first-time users | LOW | MED | Several approaches. 1: Include basic static tutorial information (e.g. 'Click button to load table info then drag fields to the selection buckets') 2: Display dynamic help information for getting a basic query off the ground (e.g. 'You added a field to the Values bucket. Add at least one column to rows/columns to trigger a pivot query.') 3: Add tooltips to interface elements. | Cancelled
49 | charts should intelligently flip x/y axes so that primary axis is always X. Like in Excel. | HIGH | MED |  | Not Started
42 | Add views, in addition to tables, to data sources | HIGH | LOW |  | Complete | 2017-10-27
46 | Chart title should be editable. Save in transform. | HIGH | MED |  | Complete | 2017-11-20 | 2017-11-20
44 | Charts should work when there are no aggregators | HIGH | LOW | Charts were incorrectly referencing model.Values to get agg list, causing NPEs. Switched to results.meta.aggregators and it's working. | Complete | 2017-11-10 | 2017-11-10
50 | User can define 'save name' for query | HIGH | MED | part of #19 | Complete | 2017-11-22 | 2017-11-22
19 | Save queries to server. | HIGH | MED | ID, QUERY_NAME, USER, MODEL, TRANSFORM, EVENT, CREATE_DATE, UPDATE_DATE, UPDATE_USER, EXPIRE_DATE, EXPIRE_USER | Complete | 2017-11-23 | 2017-11-23
45 | Should be able to sort pivot table labels. | MED | MED | Part of #48 | Not Started
48 | change field-level manipulations on pivot table to dropdown-based, like in Excel. | MED | MED | Thereby removing the mouseover buttons we currently use | Not Started
22 | Add toast notifications | LOW | MED | Toasts will give users feedback about the following: saving a query, trying to show a chart with no mostRecentResults value, successfully loaded pivot, etc. JQueryUI does not have a native toast widget. | Not Started
9 | Back-end mechanism to halt the query. | LOW | HIGH | If the associated front-end mechanism works, do we need this functionality? The only downside to letting all requests complete on the back-end is that we are wasting DB queries. Otherwise, every server request is stateless so the requests don't affect each other. | Not Started

## Sheet2
FIELD LIST
SORT BUCKETS