## Sheet1
Stage | Feature | Priority | Est. Difficulty | Approach | Status | Reference | Time
Pre-parse UI | Show UI chrome while parse request is being processed (e.g. spinner?) | LOW | LOW | Font Awesome is already a dependency and has nice animated spinners for this. Spinner will be created on request to server and destroyed on response from server. | Not started | Next
Pre-parse UI | Change query panel layout to 2 col: fields on left, sort buckets on right | MED | LOW | Flexbox | Complete | See sheet #2
Pre-parse UI | Refactor HTML and CSS to be maintainable | HIGH | MED | Old HTML/CSS grew incrementally with project. Can be rewritten now that requirements are better understood. Rewrite will be much smaller & more maintainable. Will use BEM to organzie CSS. | Complete
Pre-parse UI | Change dragging behavior so that dragged fields are cloned and instantiated on drop in sorting bucket. Ensure sync between field list and buckets. | HIGH | HIGH | Jquery includes a helper to make drag actions create a separate piece of dom attached to the mouse. Will use the field's UL element as a clone, and append a new copy to the sorting bucket on drop action. Difficulty is high because this item will require research + manual testing. | Done
Pre-parse UI | Ensure pivot configuration rules align with Excel (e.g. same field can appear in row & filter, but not row & column) | HIGH | MED | Difficulty is for researching rules to ensure all cases are covered. Rules will be implemented as predicates for each sorting bucket with the signature `canDropHere(model, fieldAskingToDrop)` which will encode rules | Started |  | 2 Day
Pre-parse UI | Add UI indicators to field list showing which fields are currently in a sorting bucket. Ensure sync between field list and buckets. | LOW | MED | Add hook to change field list DOM on (drop in sorting bucket) and (remove from sorting bucket). | Not started
Pre-parse UI | Reorganize query model to have sensible keys and pare down # of fields: { meta: { table: tableName }, query: { rows: [], columns: [], aggregates: [], filters: [] } } | HIGH | LOW | Model fns are lexically separate and each is a pure function. Will audit each fn to ensure compliance w/ model. | Tabled
Pre-parse UI | Refactor Jquery code to use module pattern, separating model operations from view operations in own name spaces to increase maintainability. | MED | MED | These sets of fns are already lexically separate. Not difficult to move into own modules. | Not started | Next
Parse | Add ability to slice pivot on multiple columns | HIGH | HIGH | Multiple columns are doable but will need to figure out how to cleanly create a string with all column combos. See https://stackoverflow.com/questions/38696067/oracle-sql-pivot-on-multiple-columns-fields | Not started
Parse | Add ability to use multiple aggregators | HIGH | HIGH | Need to research this item to confirm, but I believe it's as simple as a comma separated list of aggregator fns. Will need to figure out interactions w/ LIST UNIQUE (LISTAGG) which triggers an entirely separate subquery. | Not started
Post-parse UI | Add ability to group rows/cols | HIGH | HIGH? | Need to research item. | Not started
Post-parse UI | Add ability to sort columns by drag and drop | HIGH | MED | Simple in theory using Jquery's drag helpers. Unsure how drag helpers interact w/ table elements. | Started |  | 1 Day
Post-parse UI | Add ability to remove unwanted columns | HIGH | MED | Right-click->Remove yanks column and adds a button near the pivot table. Clicking button re-adds column to table. | Started |  | 1 Day

## Sheet2
FIELD LIST
SORT BUCKETS