## Sheet1
ID | Feature | Priority | Est Difficulty | Approach | Status | Started | Completed
3 | Change Filter selection for Filters to be similar to excel, mulit-list check boxes | HIGH | HIGH | Dropping a field into the filter bucket triggers a SELECT UNIQUE to get the field's values from the table. Have been asked to retain SQL style queries. That code is not activated right now--need to refactor a bit before it can be readded. | Complete | 2017-09-28 | 2017-09-28
2 | Save/restore queries | HIGH | HIGH | Query information is already being updated in lockstep with user actions. Trivial to store query objects (in localstorage to start with). On retrieval, fire off the stored query object and rearrange selection bucket DOM to match object. DOM arrangement will require rewriting some code in client-side View module. | Complete | 2017-08-17 | 2017-08-29
1 | Make app UI discoverable for first-time users | HIGH | HIGH | Several approaches. 1: Include basic static tutorial information (e.g. 'Click button to load table info then drag fields to the selection buckets') 2: Display dynamic help information for getting a basic query off the ground (e.g. 'You added a field to the Values bucket. Add at least one column to rows/columns to trigger a pivot query.') 3: Add tooltips to interface elements. | Not Started
6 | Limitation - Cannot do multiple aggregators at the same time, for example Count of ID and SUM of ID where Year is rows | HIGH | LOW | This is no problem on the back end. Just need to adjust front-end validation to allow duplicate field in Values bucket | Complete | 2017-08-25 | 2017-08-25
5 | Display error to user when query times out on server. | HIGH | LOW | Unsure what message CodeIgniter sends internally when request times out. Worst-case, front-end code can catch the HTTP 500 error and build an error object to show the user. | Complete | 2017-08-25 | 2017-08-25
11 | Fix 'column ambiguously defined' when aliasing long column values with aggregate fns | HIGH | HIGH | On the server, alias column/reducer names to compact representation and keep hydration mappings that can be applied to the results returned from the DB. e.g. the string "2017" is replaced with random identifier "SDKJG" wherever it occurs in the query. Before passing results back to the client, replace all random identifiers with their 'real' string representations. Also allows us to represent results in a more sophisticated way than array-of-arrays. (The term for this new representation is 'expressive results') | Complete | 2017-08-29 | 2017-09-14
20 | Add menu library to support item #s 2, 3, and context menus | HIGH | MED | Cancelled in favour of using JQueryUI's modal dialog() for #2 and #18, and expanding contextmenu.js library for #3 | Cancelled | 2017-08-18 | 2017-08-27
8 | Remove ability to drag-and-drop columns which contain row labels | HIGH | MED | N = length of rows array. First N elements of each row array do not have the sortable attribute. | Complete | 2017-08-28 | 2017-08-28
18 | Display chart representation of pivot table with chart.js. Simple bar/line charts for now. | HIGH | MED | Some data contortion required. Array of arrays not supported in the case of multiple aggregators. Also, what about case of non-numeric fields? (Labels will be improved with #11) | Complete | 2017-08-29 | 2017-08-30
7 | Count on just values when no rows or column values selected | HIGH | MED | Took this to mean 'only value(s) are selected'. Add logic to validation that does not reject this query configuration. This type of query will present a single row, COUNT(*). | Complete | 2017-08-18 | 2017-08-18
9 | Back-end mechanism to halt the query. | LOW | HIGH | If the associated front-end mechanism works, do we need this functionality? The only downside to letting all requests complete on the back-end is that we are wasting DB queries. Otherwise, every server request is stateless so the requests don't affect each other. | Not Started
4 | Research: Can we reconstruct post-query client side adjustements to the pivot table, such as removing/renaming fields, when retrieving previous queries? | LOW | HIGH | Transformations have made this possible. Transforms are included with the data saved about a query. When loaded, the transform is pulled out and combined with the pivot result when it comes back from the server. | Complete | 2017-09-12 | 2017-09-21
10 | Mouse Pointer/curser when selecting a field and dragging is showing text field cursor | LOW | LOW | Adjust jquery properties for draggable container. | Complete | 2017-08-18 | 2017-08-18
17 | Bug: identical Value entries cause 'column ambiguously defined' (e.g. COUNTOF_ID and COUNTOF_ID in Values bucket) | LOW | MED | Detect whether duplication is happening, and adjust SQL query's alias for the aggregate value. Will work best if end user never sees column aliases (current implementation of #11 doesn't deal with this, but it can be accommodated by creating different aliases if the request to register an alias came from an aggregator fn.) | Not Started
13 | Limitation - Can only do Rows and IDs not just Columns and IDs | MED | MED | Add logic to validation that does not reject this query configuration. This type of query will present a single row, COUNT(*) pivoted against SELECT DISTINCT column values. | Complete | 2017-08-18 | 2017-08-18
14 | Limitation - Removing Unwanted Rows | MED | MED | Got this for free with expressive results/transformations. See #11 | Complete | 2017-09-18 | 2017-09-18
12 | Front-end mechanism to halt the query. | MED | MED | Each query is assigned a unique ID when it is sent to server. Client maintains a buffer of pending queries. When user signals to halt current queries, results of queries in the buffer will be discarded when they return from the server. Queries made after the 'halt' command will be treated as normal. | Complete | 2017-09-06 | 2017-09-06
15 | Ability to rename row/column/aggregator labels | MED | HIGH | Will register a new transform for remapping. | Complete | 2017-09-27 | 2017-09-28
21 | Refine presentation of charts, building on #18 | MED | MED | Need improvements to chart visuals: sort entires respecting numeric columns (but see #11), make bar charts more legible. Legends take up too much space at bottom of chart. Can charts be resized? Do charts respect label renaming? Also, charts do not work with length 0 aggregators. | Not Started
16 | Revisit UX for double-click UI operations | MED | LOW | Replace double-click delete actions with an on-hover 'X' button for removing fields. Use Jquery hover() | Complete | 2017-08-31 | 2017-08-31
22 | Add toast notifications | MED | MED | Toasts will give users feedback about the following: saving a query, trying to show a chart with no mostRecentResults value, successfully loaded pivot, etc. JQueryUI does not have a native toast widget. | Not Started
19 | Logging user behavior data. Foreign key of query, and whether a chart was used (and which chart) | MED | MED | Will write a logging library that can be called with arbitrary JS objects to store information. How to generate & track user IDs? | Not Started
23 | Changes in pivot table shape (e.g. removing rows/cols/resorting) should be reflected in charts | MED | HIGH | Changes currently modify DOM, not app state. Conversely, charts are generated from state (specifically most recently received pivot results). Need to pin shape modifications to state. See #11 | Complete | 2017-09-18 | 2017-09-18
24 | Arrange table fields and sorting buckets in vertical stack | LOW | LOW | Combine container divs. | Complete | 2017-09-01 | 2017-09-01
25 | Restyle app for cohesive look and feel | LOW | MED | Redid UI to more closely match Excel ribbon idioms. Used bootstrap for element styles. | Complete | 2017-09-01 | 2017-09-06
26 | Allow user to toggle live fetching of pivot data from server | LOW | LOW | Flag will bypass call to sendConfig() in pivotController.js | Not Started
27 | Should be able to both 'save' and 'save as' queries | MED | MED | Give saved models an ID, so that new saves can overwrite current 'file' or else do a 'save as…' | Complete | 2017-09-21 | 2017-09-21
28 | Move jQuery and other external libs onto server | HIGH | LOW | Enumerate all external libs | Complete | 2017-09-25 | 2017-09-25
29 | Remove dead code from recently-changed libs | LOW | LOW | Affects tpivot and tchart | Complete | 2017-09-25 | 2017-09-25
30 | Drag and drop sorting for row/cols | HIGH | MED | Sorting done through a dedicated UI element. | Complete | 2017-09-26 | 2017-09-27
31 | Row headers should appear hierarchical like col headers | HIGH | MED | For each included row, keep track of how many contiguous values there are for each label. When iterating through rows, only draw the label (with rowspan=contiguous) when coordinateIndex % contiguous === 0 | Complete | 2017-09-26 | 2017-09-26
32 | Row/Col totals | HIGH | MED | Like excel pivot tables | Not Started
33 | Relabel save/load buttons | HIGH | LOW | Load discard save save as | Complete | 2017-09-28 | 2017-09-28
34 | Add new database location | HIGH | MED | Current DB location is somewhat hard-coded. Need to refactor some stuff to make this work. | Not Started
35 | Remove legend from graphs | HIGH | LOW |  | Not Started

## Sheet2
FIELD LIST
SORT BUCKETS